## NP Change Request Log
Change Request Number | NP Section | Policy / Area Affected | Page | Change request | Issue detail | Response | Change? | Date raised | Date change to be implemented
NP21 | 1 Introduction | Issues and Opportunities | 1 | Additional data required | No mention of the proximity of the county and national boundaries - to some extent this makes Malpas what it is. | Agreed. This would be best covered in section 2.2 (p3). It was in an earlier draft and removed, it will be re-inserted. | Y | 2014-01-19
NP36 | 1. Introduction | Picture of Jubilee Hall Clock | 1 | Picture needs a caption | Suggest "Millennium Clock on the Jubilee Hall on the High Street | We will add this as a caption. | Y | 2014-02-19
NP37 | 1. Introduction | Figure 1.1 Neighbourhood Plan Area | 2 | Add Parish Boundary line | Need to define the Malpas / Overton Parish Boundary line | I am not sure this would be helfpul. The NP area is not the same as the Parish and to show both could be confusing. The Parish boundary is not needed in this context. | N | 2014-02-19
NP15 | 2 Malpas Today | Table 2.1 | 3 | Data Error | Distance to Whitchurch On page 3 it is 8 miles whereas on page 56 it 6 miles. I think the 6 miles is correct. | We will review the distances and be consistent and accurate throughout. | Y | 2014-01-19
NP38 | 2. Malpas Today | 2.2 Site Location | 3 | add data | Plan quotes small indigenous employment base; should we define a figure | There are no reliable sources for a figure for the indigenous employment base in Malpas. It is not included within the Census data. | N | 2014-02-19
NP39 | 2. Malpas Today | Table 2.1 | 3 | Data error | Distances to various settlements are incorrect - Check AA Route Finder | See comment above (NP15) | Y | 2014-02-19
NP40 | 2. Malpas Today | 2.3 Notes on Data Sources | 4 | Data error | Some parishes missing from list some spelt wrongly | We will amend the list. | Y | 2014-02-19
NP41 | 2. Malpas Today | 2.4 Local History | 5 | Review statement | This represented the basis of a military garrison stationed here. (Do 5 Knights represent a Military garrison | Yes, 5 knights would be accompanied by a much larger number of men-at-arms and archers and would represent a significant military garrison. | N | 2014-02-19
NP16 | 2 Malpas Today | 2.4 Local History | 6 | Data Error | Date of Closure of Malpas Station The station closed in 1957 and the railway line closed to goods traffic in 1963. | We will amend this. | Y | 2014-01-19
NP42 | 2. Malpas Today | 2.5 Evolution of the Settlement | 7 | Table Reference error | Reference to table 2.5 is incorrect | We will correct this. | Y | 2014-02-19
NP43 | 2. Malpas Today | 2.5 Evolution of the Settlement | 7 | Word check | (although there have been infill sites and more dispersed development in all eras) should this read eras or areas? | It should read "eras". | N | 2014-02-19
NP10 | 2. Malpas Today | Figure 2.5 | 8 | Question | What is the significance of the red Site Boundary line | This has been retained from the Malpas Character Study. We agree that it is not relevant here and it will be removed. | Y | 2014-01-16
NP116 | 2. Malpas Today | Figure 2.5 | 8 | Clarity of data | The red edge on this plan is described as the Site Boundary. I assume that this relates to the study area for Malpas. Perhaps the meaning of this red line could be made a little clearer in future versions of the plan. | See above. | n/a | 2014-02-23
NP44 | 2. Malpas Today | 2.5 Evolution of the Settlement | 9 | Reference to table 2.2 | Analysis of the figures in table 2.2 reveals a percentage reduction in development over each 30 year period. Should we review the housing figure with regards to this and the 340 dwellings already given permission | Neighbourhood Plans are not permitted by legislation to reduce the housing figure set by the local authority, only to increase it. We will have to reflect the figure stated in CW&C's Local Plan. | N | 2014-02-19
NP45 | 2. Malpas Today | 2.6 Village Character | 10 | 2nd bullet point | Do not understand the statement High Street North; is this actually Tilston Road? | No, "High Street North" is a character area which has been defined and mapped in the Malpas Character Study. This is expalined in the first parapgraph under 2.6 and the preceding bullet point but it will also be stated more clearly in this bullet. | Y | 2014-02-19
NP46 | 2. Malpas Today | 2.7 Malpas and Overton Today 12 Key Points | 10 | Key point 2 Table Reference error | Should the reference be (see table 2.5) no (see Table 2.4) | Yes, we will correct this reference. | Y | 2014-02-19
NP35 | 2.7 Malpas and Overton Today 12 Key Points | Key point 5 | 11 | Resolution required | How do we keep the figures current in this key point | Good question - the figure here can only be a point in time. This will be removed to prevent NP becoming dated. | Y | 2014-02-19
NP47 | 2. Malpas Today | 2.7 Malpas and Overton Today 12 Key Points | 11 | Key point 6 | There are 344 (34%) economically inactive people in the parish - should we be highlighting this as significant | We have had commentary on these figures from a Demographic Analyst at CW&C now. The national figure for economic activity is 30.1%, so Malpas is similar and so this is not significant. Economically inactive people in Malpas are mostly retired people. | N | 2014-02-19
NP48 | 2. Malpas Today | 2.7 Malpas and Overton Today 12 Key Points | 11 | Key point 6 | The census shows 29.9% of all economic inactive residents received - Is this a ward figure or parish? | This figure is incorrect and needs revising following comments from the Demographic Analyst at CW&C. We will be using Ward figures wherever possible. | Y | 2014-02-19
NP49 | 2. Malpas Today | 2.7 Malpas and Overton Today 12 Key Points | 11 | Key point 6 | Abbreviation DWP needs to be explained in Glossary | We will either add this to the Glossary or spell out in full here. | Y | 2014-02-19
NP50 | 2. Malpas Today | 2.7 Malpas and Overton Today 12 Key Points | 11 | Key point 6 Table Reference error | Miss alignment in table references | We will correct this. | Y | 2014-02-19
NP51 | 2. Malpas Today | 2.7 Malpas and Overton Today 12 Key Points | 11 | Key point 7 | Do not recognise Chester Villa on High Street | This is the name on the national listing for this building and on OS mapping. It is a detached Georgian house facing the junction with Chester Road. We are not aware of another name for it. | N | 2014-02-19
NP120 | 2. Malpas Today | Key point 4 | 11 | Consideration of data | Should we be quoting "average" house prices? | This is a valid data source, average house prices are commonly used, and vital evidence for our policy on affordable housing (H3). | N | 2014-02-22
NP9 | 2. Malpas Today | Fact number 9 | 12 | Spelling Error | Elementary is misspelt on the Occupations Chart | We will correct this. | Y | 2014-01-16
NP52 | 2. Malpas Today | 2.7 Malpas and Overton Today 12 Key Points | 12 | Key point 7 | Old School House is on Tilston Road not High Street | We will correct this. | Y | 2014-02-19
NP53 | 2. Malpas Today | 2.7 Malpas and Overton Today 12 Key Points | 12 | Key point 10 | Hampton Heath Industrial Estate; Distances need checking with AA Route Planner | We will review and amend. | Y | 2014-02-19
NP54 | 2. Malpas Today | 2.7 Malpas and Overton Today 12 Key Points | 12 | Key point 11 | How can we improve access to Superfast Broadband - when we don not have it in the village | We will amend this to read "provide" rather than "improve". | Y | 2014-02-19
NP55 | 2. Malpas Today | 2.7 Malpas and Overton Today 12 Key Points | 12 | Key point 12 Table Reference error | Miss alignment in table references | We will correct this. | Y | 2014-02-19
NP121 | 2. Malpas Today | Key point 12 | 14 | Insert words | (see Table 2.6) But 20% are transported by car and alongside staff travel | We will add the reference. 20% is relatively low compared to other schools so "and" is more appropriate than "but". | Y | 2014-02-22
NP122 | 2. Malpas Today | Key point 12 | 14 | Insert words | that use the B5069 and B5395 passing through the centre of the village | Ok, we will amend this. | Y | 2014-02-22
NP12 | 3 Developing the Neighbourhood Plan |  | 15 | Punctuation error | This has informed the vision and objectives within this Plan and where clear consensus was found, | "This has informed the vision and objectives within this Plan, and where clear consensus was found" | Y | 2014-01-19
NP56 | 3 Developing the Neighbourhood Plan |  | 15 | Consider Deleting section | How relevant to the final document is the process identified in this section. This should perhaps be an appendix if we need it at all | It is best practice within NPs to include this section and other NPs have this (including adopted ones). It is useful for the general reader to understand the process and where the policies have come from. The section is only 2 pages long, and central to the NP, so thought best to include it here rather than as an appendix. The structure of the document was agreed with the Streering Group and CW&C at an early stage. | N | 2014-02-19
NP119 | 3. Developing the Neighbourhood Plan | All | 15 | Explanation required | The plan looks very comprehensive and well supported by evidence. My only comment is that on page 15 the flowchart shows stage 4. Generating options but it isn’t clear in the plan how this stage was addressed. You might well have explored options through the vision & objectives survey but you could clarify this in the text. | Agreed. We will add more text on the Options stage. | Y | 2014-02-24
NP7 | 4 Vision and Objectives | The Vision | 17 | Wording Change | Celebrated, making the are an attractive place to live and visit. | We will change to "...celebrated, making the area an attractive place in which to live, work and visit." | Y | 2014-01-14
NP57 | 4 Vision and Objectives | Objectives | 17 | Objective 2 addition of word | To ensure that new development is sustainably located, connected and integrates well with the village | Agreed. | Y | 2014-02-19
NP58 | 4 Vision and Objectives | Objectives | 17 | Objective 8 addition of word | To support a broad and sustainable local economy that provides job opportunities for residents of Malpas and Overton | Agreed. | Y | 2014-02-19
NP59 | 5.1 Homes for all | Whole Section | 18 | Missing Section heading | This section should have an overarching heading e.g. 5 The policies | Agreed. | Y | 2014-02-19
NP60 | 5.1 Homes for all | Objectives | 18 | cross reference missing | Each set objectives for each of the policy themes should have a note cross referencing them to Section 4 Vision and Objectives page 17 | Agreed. | Y | 2014-02-19
NP123 | 5.1 Homes for all | Issues and Opportunities | 18 | Replace a word | 1st Paragraph - replace the word village's "status" with village's designation. | Agreed. | Y | 2014-02-22
NP61 | 5.1 Homes for all | Evidence Base | 19 | cross reference missing | the process for the update of both the Neighbourhood Plan and the evidence based document need to be captured under "section 6 making it happen" - it is not clear at present | The need for review and update is mentioned both here and in Section 6. The NP does not need to state the timetable and process for doing this. This will be for the Steering Group to determine. Describing this here could be inflexible and subsequent review may fail to meet the process and periods set out. We do recommend that the Steering Group agree a timetbale though. The adoption process for an updated NP will be the same as for the NP production itself. We will add some more text on updating evidence base and reviewing what may need to change in the NP and cross reference between H1 and Section 6. | Y | 2014-02-19
NP124 | 5.1 Homes for all | Evidence Base | 19 | Amendment | Indicate that the Village Design Statement is "draft" | OK - but this will weaken its credibility - can the Parish Council issue it as final version? I suggest it is either described without "draft" or not referred to at all. | N | 2014-02-22
NP13 | 5.1 Homes for all | Evidence base | 20 | Data error | "6 x 1-bed dwellings, 5 x 2-bed dwellings, and 3x1-bed dwellings ..." something is wrong with this. | There is nothing incorrect here. These are the correct figures from the SHMA - a total of 16 dwellings, with the mix of sizes stated, required each year. | N | 2014-01-19
NP62 | 5.1 Homes for all | Evidence Base | 20 | bullet point 3 data references | "543 houses in Malpas are classed as being" - Is this ward or parish data? | This is a Parish figure, but we will replace this for the Ward figure (241) and make this clear. | Y | 2014-02-19
NP125 | 5.1 Homes for all | Evidence Base | 20 | Replace a word | Last paragraph - replace the words the population accommodates to the population includes | Agreed. | Y | 2014-02-22
NP126 | 5.1 Homes for all | Evidence Base | 20 | Insert a word | Last paragraph - insert the word "may be the establishment" | Agreed. | Y | 2014-02-22
NP63 | 5.1 Homes for all | H1 New housing | 21 | Consider inserting Housing number | Consider reviewing quantum of housing rather than pointing at STRAT 8 | See comment NP44 above. | N | 2014-02-19
NP64 | 5.1 Homes for all | All | 21 | Name Change | References throughout the plan to the Neighbourhood Forum. Malpas is not a Neighbourhood Forum it is a Neighbourhood Steering group. A Forum is where no parish council is involved and at least 21 people have to be associated with a Neighbourhood Forum for it to be legal and recognised | This comment is correct. We will amend the reference. The correct terminology in this context should be to Malpas Parish Council and Overton Parish Council as "Steering Group" has no meaning in terms of Neighbourhood Planning legislation. Elsehwere we will refer to the Steering Group. | Y | 2014-02-19
NP114 | 5.1 Homes for all | H1 | 21 | Data required | In paragraph 30 of the Gladman judgement, the Inspector emphasised the fact that the neighbourhood Plan "as it currently stands" does not set a maximum housing figure. I read this as a hint that it should - particularly when the possibility of applications under H2III would increase the numbers yet further. | This is interesting, we will need to monitor developments on the Local Plan adoption and reflect what the final version says. The figure for Malpas is expressed as a "maximum" though and our will continue to reference the Local Plan without stating the number (see comment NP150 below). | N | 2014-02-22
NP117 | 5.1 Homes for all | H1 | 21 | Retention of policy | The approach adopted by Policy H1 is considered to be pragmatic and is welcomed. It is acknowledged that Policy STRAT 8 of the Cheshire West and Chester Local Plan will set out housing requirements for Malpas once adopted. However, reference to additional housing beyond this number potentially being permitted is welcomed and should be carried forward to the final version of the Neighbourhood Plan. This will be critical to ensuring that further appropriate development can continue to come forward that enables the development of local services, facilities and infrastructure. | This has been reviewed further at the meeting of the Steering Group on 5/3/14. It was agreed that in the context of the number of homes already granted planning permission, and the 30% affordability requirement that applies to these, that the need for affordable housing had been met and that this element of Policy H1 will now be removed. | Y | 2014-02-23
NP127 | 5.1 Homes for all | H1 New housing | 21 | Replace words | 2nd paragraph - Change the wording from "It is recognised that new development will be required to extend the existing" to "It is recognised that new development will necessitate extending the existing" | Agreed. | Y | 2014-02-22
NP128 | 5.1 Homes for all | H1 New housing | 21 | Change of words | 3rd paragraph - Change the word "supports" to "accepts" the current target. | The Neighbourhood Plan has no choice, legally, than to 'accept' the target, stating so is superfluous. Stating "support" is stronger and will give increased weight to CW&C's figure which will assist in them refusing applications locally that exceed the target. | N | 2014-02-22
NP129 | 5.1 Homes for all | H1 New housing | 21 | Change of words | 3rd paragraph - Change of word (potentially including Brownfield sites) Whilst the Neighbourhood - Change "Whilst" to "Although" | Agreed | Y | 2014-02-22
NP150 | 5.1 Homes for all | H1 New housing | 21 | Policy Re-write | The word quantum needs to be replaced by a maximum number. In the inspectors report on the Gladman’s appeal he was unable to give weight to the NP because it didn’t have a maximum number of houses. In CWAC’s Local Plan STRAT 8 the sustainable maximum number for Malpas is 200. I therefore think that we should adopt this. CWAC go in to list exceptions where this number can be exceed for redevelopment, conversion of buildings and infilling. In our NP, the second exception listed worries me, because I think that it could leave planning authorities no option but to accept a major development where the developer has promised to deliver an aspiration. The majority of our aspirations are major items and in order to deliver this a developer would need to build a lot of houses in excess of 30 set down in the Plan. For example the Egg packing station is going to deliver a car park but the developer has permission for 60 house. The Cockfight field has planning for 41 houses and has made land available for a surgery. In view of the 340 houses which already have planning I think we need to tighten this clause up. Can I therefore suggest that we adopt CWACs exceptions to read “ a housing development that enables the delivery of other community aspirations as set out in this document ( see Aspirations sections 5.4 and 5.4) where the development does not exceed 30 dwellings. | As discussed above the NP will reflect exactly what the Local Plan says in terms of a housing number for Malpas. As the Local Plan is currently undergoing its adoption process this number is likely to change and cannot be known at this moment. For this reason the NP will refer to the number in the Local Plan without actually stating the number. This also provides flexibility in case this number changes during the life of the NP. This approach was agreed at the Steering Group meeting on 5/3. The second part of this policy relating to exception sites will now be removed (see comment NP17 above). | N | 2014-02-26
NP65 | 5.1 Homes for all | H1 New housing | 22 | Explain SOC | Explanation of SOC1, SOC2 and SOC3 required in Glossary | These are Local Plan policy references, This is made clear in the policy text. The Glossary is not the right place to explain this and would have nothing further to add - they are simply a reference code used in the Local Plan. | N | 2014-02-19
NP130 | 5.1 Homes for all | H2 Rural Housing Development (iii) | 22 | Change of words | Delete the word innovative | We believe that "innovative" is a key part of this criteria. This reflects the wording in the NPPF and will ensure that the bar is set high to allow only the highest quality development, which can represent exemplar designs. | N | 2014-02-22
NP131 | 5.1 Homes for all | H2 Rural Housing Development (iii) | 22 | Change of words | Change wording from "standards in the rural area. The design must also be sensitive" to "standards in the rural area, while being sensitive" | Disagree. This criteria is about only allowing housing development that will increase design standards in the rural area (see comment above). Policy LC1 deals with new development beong sensitive to established character. | N | 2014-02-22
NP118 | 5.1 Homes for all | H4 | 23 | Retention of policy | The acknowledgement that some schemes will be larger than 30 units is supported along with the need for character areas within schemes where more than 30 units are proposed. The overall supportive approach adopted by the Plan to new development, which is of an appropriate scale and within suitable locations is strongly supported. It is critical that this approach is maintained with future iterations of the Plan to ensure that new services and facilities can be provided for. | Noted. | N | 2014-02-23
NP132 | 5.1 Homes for all | H3 Housing Type and Tenure | 23 | Change of word | Bottom of first column - change "residents that wish" to "residents who wish" | Agreed. | Y | 2014-02-22
NP154 | 5.1 Homes for all | H3 Housing Type and Tenure | 23 -24 | Addition to Policy | Include reference that affordable homes should be pepperpotted - scattered in viable blocks across the development site or such wording that prevents them being built in a single cluster | We will add some text on this. | Y | 2014-03-04
NP66 | 5.2 Built Character and Local Environment | Issues and Opportunities | 26 | Additional data required | CWaC are preparing a Malpas Conservation Area Appraisal - Do we know when this will be delivered and where/how do we reference these documents | We have had feedback on this from CW&C and will make the necessary cross-reference. | Y | 2014-02-19
NP68 | 5.2 Built Character and Local Environment | BE1 | 28 | in-correct reference | Makes a reference to Policy H6 which does not exist | We will correct this. | Y | 2014-02-19
NP69 | 5.2 Built Character and Local Environment | BE1 | 28 | Missing data? | BE1 is intended to cover significant non-residential schemes - Where have we covered commercial schemes? | BE1 will be amended to cover all 'development' generally. | Y | 2014-02-19
NP70 | 5.2 Built Character and Local Environment | BE2 | 30 | References | There are references to "High Street North" at various locations in the plan. This should read Tilston Road | The reference is deliberate. High Street North is the name of a character area as described in the Malpas Character Study and is not the same as Tilston Road generally. This is clealry explained in the text. | N | 2014-02-19
NP34 | 5.2 Built Character and Local Environment | BE5 | 32 | Process for assessing potential; archaeology sites | Request that policy be re-written to include a requirement to "plough" turn the top ground over and then "field walk" and metal detector sweep before determination of action on potential sites as identified in Figure 5.2 "Areas of Archaeological Interest" | It is not the place of a NP policy to set out how exactly an archaeological investigation should be done. The approach for each site should be agreed between appropriately qualified specialists and CW&C Archaeology under existing processes and policies. | N | 2014-02-19
NP133 | 5.2 Built Character and Local Environment | BE5 Archaeology | 32 | Change of word | top of second column - Change the word "the Parish Council who holds" to "the Parish Council which holds" | Agreed. | Y | 2014-02-22
NP71 | 5.3 Landscape Character and the Natural Environment | Voice of the Community | 36 | delete public comments | Delete comment " maintain views and vistas across open countryside" This is duplicated | Agreed. | Y | 2014-02-19
NP72 | 5.3 Landscape Character and the Natural Environment | LC1 Landscape Character and Development | 36 | Material correction | I think Cheshire Estate Railings are know as just Cheshire Railings | The correct term is Cheshire Estate Railings. | N | 2014-02-19
NP134 | 5.3 Landscape Character and the Natural Environment | Artificial Habitats | 36 | Change of word | top of 1st column - Change "Man's imprint" to "Human imprint" | Agreed. | Y | 2014-02-22
NP152 | 5.3 Landscape Character and the Natural Environment | LC1 Landscape Character and Development | 36 | Policy addition | External Lighting to be non sky pointing | The correct term is "downlighting" - we will add this. | Y | 2014-03-01
NP73 | 5.3 Landscape Character and the Natural Environment | LC2 Renewable Energy | 38 | Policy Re-write | Wording is cumbersome and not clear - re-write | This policy is being reviewed and will be rewritten. | Y | 2014-02-19
NP74 | 5.3 Landscape Character and the Natural Environment | LC2 Renewable Energy | 38 | re-write | Fall over distances quoted do not read right. Also bullet points are miss-aligned | See above. | n/a | 2014-02-19
NP75 | 5.3 Landscape Character and the Natural Environment | Aspirations | 41 | Picture Caption required | Picture caption required suggest " Mares Tails" (Cirrus Uncinus clouds) progressively invading the sky over the "Twelve Apostles" footpath across the OxHays | We will add a caption (maybe a less poetic one!). | Y | 2014-02-19
NP135 | 5.3 Landscape Character and the Natural Environment | Aspirations | 41 | Insert words | insert the words " off road cycleway" after sculpture trail | Agreed. | Y | 2014-02-22
NP136 | 5.3 Landscape Character and the Natural Environment | Aspirations | 41 | Insert words | at the end of the paragraph insert the words ecology, perhaps demarking the Overton and Malpas Neighbourhood Plan "?" boundary, preventing ribbon development that would eventually merge Malpas with for example Nomansheath and Hampton | Disagree. The comment here relates to the use of green space to prevent settlements merging (similar to green belt policy). This is best covered by development policies such as H1 and the site assessment matrix. This aspiration is about creating green corridors for amenity/ecology value, which is a different matter and should not be used to control development (not least because it is an 'aspiration' not a 'policy') | N | 2014-02-22
NP137 | 5.4 Services and Facilities | Issues and Opportunities | 42 | Change of wording | 1st paragraph - replace the words "range of services" with "range offered" | Agreed. | Y | 2014-02-22
NP138 | 5.4 Services and Facilities | Issues and Opportunities | 42 | Change of wording | 2nd column, 4th paragraph - Change wording from "It is recognised that new" to "It is hoped that new" | New development will by definition increase catchmemt population; one would hope (and reasonably expect) it will also increase local spending. This will be clarified. | Y | 2014-02-22
NP139 | 5.4 Services and Facilities | Issues and Opportunities | 42 |  | 2nd column, top of the page - Challenge the reasons indicated above are the reasons why CWaC has designated Malpas as a Key Service Centre. | This reflects the explanation from emerging Local Plan documents. The NP must reflect local policy. These reaons appear to be a logical basis for designation Malpas as a key Service Centre. | N | 2014-02-22
NP140 | 5.4 Services and Facilities | Issues and Opportunities | 42 | Remove wording | 2nd column, top of the page - remove the wording "This status is important to" and replace with "and" | Agreed. | Y | 2014-02-22
NP29 | 5.4 Services and Facilities | Education Facilities | 43 | Missing data | On page 45 the local schools are listed, but Beeches Pre School doesn't appear. Although based in Edge, a large number of people live in Malpas (it did used to be in the village some years ago). | The list is not intended to be exhaustive. Pre-schools should be excluded (we will also remove Barika). They will be added to the Evidence Base document. | N | 2014-02-05
NP76 | 5.4 Services and Facilities | Evidence Base | 44 | Consider data inclusion | Should we include the name of the restaurant's i.e. Table at Eatons, Oakdens and Grillworx? | No, restaurants tend to change names and owerships relatively frequently and these restaurants could change name during the life of the NP (possibly 10-15 years). The names are not necessary here and could result in the NP appearing dated. | N | 2014-02-19
NP77 | 5.4 Services and Facilities | Deficiencies and Capacity Education facilities | 44 | Consider data inclusion | Should we mention that due to parental choice, 40% of the pupils attending Bishop Heber currently live outside the Local Authority catchment area? | If we quote this figure we need to accuraretly reference it. Could the person who made this comment please supply the relevant data source please? | tbc | 2014-02-19
NP78 | 5.4 Services and Facilities | Deficiencies and Capacity Education facilities | 44 | Consider re-write | The Primary school is close to capacity "and has no space on the current site for building extensions" | We will amed this to refer to "limited space for extensions". | Y | 2014-02-19
NP141 | 5.4 Services and Facilities | Existing Community Facilities | 44 | Consider removing | 1st Column 2nd paragraph repeats what has been said before | Disagree - this paragraph makes some valid points about accessibility that are not included elsewhere. | N | 2014-02-22
NP142 | 5.4 Services and Facilities | Deficiencies and Capacity Community Facilities | 45 | Question | 2nd column, 2nd paragraph - last sentence - has this been resolved now with the latest planning application for the Cockfight filed? | We will review this planning application and reference accordingly - but until planning permission has been granted and the facility built we should still reflect the aspiration. | Y | 2014-02-22
NP143 | 5.4 Services and Facilities | Deficiencies and Capacity Retail | 45 | Remove wording | 2nd column, last paragraph - remove the words "A petrol station once existed in the village and for many | Maybe "in the Neighbourhood Plan area" instead of "in the village" - we can't just say "a petrol station once existed"! Key point is that there was one here. | Y | 2014-02-22
NP79 | 5.4 Services and Facilities | Deficiencies and Capacity Sport and Recreation | 46 | Data error | Christleton is 13 Miles north of maples (AA Route Planner) | We will correct this. | Y | 2014-02-19
NP115 | 5.4 Services and Facilities | Voice of the community | 46 | Data required | I can not recall any reference to concerns about flooding and drainage, which is a major issue for some residents. | Flooding and drainage is extensively covered by existing legislation and the requirements for flood risk assessments and consultations with the Environment Agency on planning applications. There is nothing of significant value that the NP could add to this. There are no rivers here so it is not as major an issue in comparison to other NP areas. | N | 2014-02-22
NP144 | 5.4 Services and Facilities | Deficiencies and Capacity Sports and Recreation | 46 | Remove wording | Swimming Pool - The nearest ones are at Whitchurch (6 miles) and Christleton ( 13 Miles ) | We will amend as suggested. | Y | 2014-02-22
NP159 | 5.4 Services and Facilities | Voice of the community | 46 | Suggested inclusion | Drainage - It is essential that as in the Gladman Appeal, the inspector stated that balancing ponds and drainage are in place before any development commenced. This should be written as part of our policies | See comment NP115. | N | 2014-03-05
NP1 | 5.4 Services and Facilities | SF1 Village Centre | 47 | Policy not in conformity with NPPF | Concern over the reference to demonstrating ‘exceptional circumstances’ for A1 to A5 uses outside of the village centre. Whilst the principle of this policy is fine, in ensuring that town centre uses are located within the village centre to maintain the vitality and viability of the centre, the wording of the policy is not in conformity with the NPPF or Local Plan. | Suggest that a sequential approach is used in the policy rather than exceptional circumstances. This would require any application for town centre uses outside of the village centre (A1 retail etc.) to demonstrate that they have considered all potential in centre and edge of centre sites first. This would ensure that sites within the village centre remain the preferred location for A1 to A5 uses and only where no alternative sites in centre are suitable, available and viable would edge and then out of centre sites be permitted. This would ensure the policy is in conformity with the approach advocated nationally in the NPPF, the current Chester Local Plan and the emerging CWAC local plan. | Y | 2013-12-05
NP31 | 5.4 Services and Facilities | SF2 Church Street | 47 | Missing data | There is no comment about the traffic coming from Church Street into the village centre. How do you propose to deal with this? | Traffic is covered by policies in Section 5.6. Policy TC1 proposes a Village Travel Plan, which will deal with all traffic in the village holsitically. | N | 2014-02-07
NP80 | 5.4 Services and Facilities | Policy SF1 | 47 | Context | Page 47, just above policy SF2 do not understand the context of the word "interpretation" | "Interpretation" in the context of tourism means information on local wildlife, wlaking/cycle routes, local history etc - this could be on signboards, plaques on buildings, leaflets, digitally etc. This is a common phrase in this context. | N | 2014-02-19
NP81 | 5.4 Services and Facilities | Policy SF4 | 48 | none | This policy reads well giving a clear objective of the policy. This is not necessarily the case with all other policies in the document | Noted. Policy wording will be reviewed throughout. | Y | 2014-02-19
NP14 | 5.4 Services and Facilities | Recreation Ground | 49 | Standardisation | "CW&C" should be "CWaC" to standardise the abbreviation. | Agreed - we will standardise throughout. | Y | 2014-01-19
NP27 | 5.4 Services and Facilities | Recreation Ground | 49 | Standardisation | "CW&C" should be "CWaC" to standardise the abbreviation. | Agreed - we will standardise throughout. | Y | 2014-01-31
NP82 | 5.4 Services and Facilities | Aspirations Recreation Ground | 49 | Explanation required | Do we need to explain "Green Flag" status? | Green Flag will be added to the Glossary. | Y | 2014-02-19
NP145 | 5.4 Services and Facilities | Aspirations | 49 | Insert words | "Long term" funding to support the Young Persons Centre and youth services | Funders and stakeholders are unlikely to provide "long term funding". The wording is best left generally as "funding". | N | 2014-02-22
NP83 | 5.5 Supporting the Local Economy | Issues and Opportunities | 50 | Explanation required | 2nd paragraph beginning "Tourism is an important… Don't understand how the Parishes remaining an attractive place to live and work will ensure it is a sustainable community | Sustainable communities (that that can continue to flourish into the long term and not decline) are considered to be those with a good mix of population; in a place that provides opportunities to live, to work and to enjoy leisure time. The place must continue to be attractive to live in, or else people will move out and the population will decline - making it harder to support shops and services. Local employment is a factor in that attractiveness and having people work in the village also increases local spending and benefits the local economy. "Sustainable community" will be added to the Glossary. | Y | 2014-02-19
NP84 | 5.5 Supporting the Local Economy | Issues and Opportunities | 50 | Clarification required | 2nd column bottom of 1st paragraph beginning "There are several tourist attractions… This gives the impression there are many employment opportunities | Disagree - I think it is clear from the attractions listed that they will not employ many people. The key opportunity for the local economy is to capture some of this visitor spending - i.e. In cafes/restaurants in the village. We will add a sentence to make this point. | Y | 2014-02-19
NP85 | 5.5 Supporting the Local Economy | Evidence base Access to Employment | 51 | Improve Picture Caption | Can we name this place? Kidnal Manor / Grange? | I don't think the picture necessarily needs a specific caption. Also there is a privacy issue - the landowner may not want their property named. It is included to make a general point, as reflected in the current caption. | N | 2014-02-19
NP146 | 5.5 Supporting the Local Economy | Evidence base Access to Employment | 51 | Insert word | most commuting is by car, but 18% of households | The figure is actually relatively low - in the UK in general 27% households do not have access to a car - so "but" cannot be justified here. | N | 2014-02-22
NP86 | 5.5 Supporting the Local Economy | Policy LE1 Explanation | 52 | Align statements | 1st paragraph beginning "Whilst it is recognised… This paragraph would appear contradictory with regards to the volume of employment opportunities | Disagree - I think this is clear: Malpas is not a strategic location for employment, and does have a high volume of employment opportunities - but there is a small business employment base which is significant locally. | N | 2014-02-19
NP87 | 5.5 Supporting the Local Economy | Policy LE2 Explanation | 53 | Clarity of linkage | Unsure how the last sentence " This includes visits to both the village centre and to the surrounding rural area links to employment | The link from tourism to the local economy (and therefore jobs) is explained under comment NP84 above. It is important to establish that this tourism opportunity includes the rural area as well as the village in order to support Policy LE2. | N | 2014-02-19
NP88 | 5.5 Supporting the Local Economy | Aspirations Home working | 53 | Clarity of linkage | Unsure how the paragraph links to Home working | Having this aspiration stated will help home workers if/when they make planning applications connected to their business. Improving superfast broadband accessibility will be of great benefit to most home businesses, especially within a rural area that lacks effective transport connections. | N | 2014-02-19
NP89 | 5.6 Transport and Communications | Issues and Opportunities | 55 | Additional wording | Insert the words " Two "B" classified Roads into the second sentence | Agreed. | Y | 2014-02-19
NP147 | 5.6 Transport and Communications | Issues and Opportunities Roads and Traffic | 55 | Change of wording | Change wording from "Today, a significant amount of through traffic still passes through the village but its roads" to " Today there is still a significant amount of this, but its roads" | Disagree. I think original wording reads better and the intended meaning is slightly different (i.e. Less important as a 'stopping place' today but still carries through traffic"). | N | 2014-02-22
NP157 | 5.6 Transport and Communication | Issues and Opportunities | 55 | Question | Parking outside the Heber school =- An accident last week involving 5 cars - Is there any way the NP can include provision for parking of Parents / Students? | This should be picked up as part of the Village Travel Plan. | N | 2014-03-05
NP17 | 5.6 Transport and Communications | Bus Services | 56 | Add additional data | Bus service - No mention that the buses no longer go to the Whitchurch station and that they never co-ordinated with the trains. This is a major transport failing keenly recognised. Bus services are subsidised by other councils and without their help Malpas is cut off from some amenities. | We will add the additional information on bus services, but a NP cannot require a local authority to subsidise bus services - and we need to consider the context of large scale funding cuts that CW&C are experiencing. | Y | 2014-01-19
NP28 | 5.6 Transport and Communications | Car Parking | 56 | Additional data required | I am a full-time wheelchair user and resident of Malpas. I would like to see it added to the comment on the provision of accessible parking that this should include accessible parking for wheelchair users with a suitable wheelchair transfer space next to it, rather than simply reserved spaces for Blue Badge holders, most of whom can walk. As a vision for the future, I would like to see parking reserved specifically for wheelchair users in addition to that for generic Blue Badge holders, who only require a parking space near to services, rather than a wheelchair transfer space. It is a constant frustration when wheelchair accessible spaces are taken by Blue Badge holders who don't need a transfer space, as I cannot then park - I can't take the risk of being blocked in as I need to open my door fully to access my car. In addition, I would like to see more public buildings become fully accessible to wheelchair users in the future. | Agreed. This will be added to the Aspirations. | Y | 2014-02-05
NP90 | 5.6 Transport and Communications | Issues and Opportunities Bus Services | 56 | Additional Information | Two observations on the sentence " There is no rail station in the area… Distance quoted conflicts with that quoted in table 2.1 on page 3 Additional information needs adding. i.e. and there is no direct bus route to the station from the village | This will be reviewed and amended. | Y | 2014-02-19
NP91 | 5.6 Transport and Communications | Issues and Opportunities Footpaths, Cycle ways and Bridleways | 56 | consider re-write | The sentence under the Leech Lane picture Suggest re-writing the beginning of the sentence to " In the wider rural area there are a few good link routes on quieter roads including... | We will lengthen this caption (though the picture is in the village not the wider rural area). | Y | 2014-02-19
NP22 | 5.6 Transport and Communications | TC1 Village Travel Plan | 57 | I would like to contribute to the travel plan | The lack of taxis, buses and safe walking and cycle routes has an impact at one end. Rail travel at Whitchurch and Chester are impacted by regional developments such as Northern Hub and national developments such as HS2. HS2 would have a fairly local impact because it would allow capacity on the West Coast main line for direct London trains from Shrewsbury and maybe Wrexham. | This should be picked up as part of the Village Travel Plan. HS2 impacts are likely to be 20 years away - too distant for this NP, and re-routing train services is beyond the scope of the NP. | N | 2014-01-19
NP92 | 5.6 Transport and Communications | Issues and Opportunities Fibre Optic broadband | 57 | Consider CIL inclusion | If Fibre Optic Broadband is a major priority should it not be included under the CIL list in this section? | CIL/s106 spending can only mitigate for the additional infrastructure that is necessiatted by the development. Providing new fibreoptic broadband is an aspiration that would not fall into this category. This may change during the life of the NP as fibreoptic broadband becomes considered more essential. New Homes Bonus spending could potentially be used for this though. Malpas Parish Council should discuss this further with CW&C. | N | 2014-02-19
NP2 | 5.6 Transport and Communication | TC1 Reasoning | 58 | Wording Change | Malpas suffers from through traffic resulting from the confluence of several roads on its eastern side (Tilston Road, Chester Road, Well Meadow, Oldhall Street, Whitchurch Road). The lack of alternative routes means that congestion in the Village Centre is worsened by drivers that are forced to pass through the Village Centre. A road link between some or all of these roads would therefore help to address the issue and help overcome traffic barriers to development. | Malpas suffers from through traffic resulting from the confluence of 5 roads (Tilston Road, Chester Road, Cross o' th' Hill, Whitchurch Road and Wrexham Road) The lack of alternative routes means that congestion in the Village Centre is worsened by drivers that are forced to pass through the Village Centre. Opportunities to link these roads should be thoroughly assessed. | Y | 2014-01-09
NP32 | 5.6 Transport and Communications | TC1 support statements | 58 | Missing data | What chance will we have to construct an Eastern Link road due to CWaC never financing it? | The funding for a new link road is unlikely to come from CW&C. It would have to be funded from new development. The likelihood of achieving this is very low. | N | 2014-02-07
NP93 | 5.6 Transport and Communications | TC 1 Explanation | 58 | word contradiction | Top of the page - the inclusion of piecemeal and cumulative in the same sentence appear contradictory | This will be clarified - the issue is that transport assessments have been piecemeal but the traffic impacts of development are cumulative! | Y | 2014-02-19
NP94 | 5.6 Transport and Communications | TC 1 Explanation | 58 | reference inclusion | 2nd paragraph beginning " Developers and Transport consultants… Include a reference to improving safety. Also include a reference to the Parish Council carrying out data gathering exercises | Agreed. | Y | 2014-02-19
NP95 | 5.6 Transport and Communications | TC 1 Explanation | 58 | Data error | Column 2, 2nd paragraph - Malpas suffers from through traffic resulting from the influence of several roads on all sides of the village i.e. Tilston Road, Chester Road, Well Meadow/Cross o' th' Hill, Whitchurch Road and Wrexham Road | Agreed | Y | 2014-02-19
NP151 | 5.6 Transport and Communications | TC1 Village Travel Plan | 58 | Question | Link Road I was under the impression that this was an aspiration and not a policy. In the travel plan it is listed as an aspiration and not a policy. However it does look like becoming a reality as the Inspector said that there should be a link road through the Gladman’s site. I am worried that any such road will result in traffic being sent along Springfield which is a residential area with on street parking and a green space adjacent to the road. Significant increase in traffic could lead to serious congestion and make the are unsafe for children to play. | The link road is an aspiration and not a policy - see revised wording of this aspiration at comment NP3 below. The road through the Gladmans site, even if it becomes a through road, will not be of the scale of a 'link road'. Any issues related to the Gladman road should be dealt with in the planning process for this application (including at reserved matters stage) rather than through the NP. | N | 2014-02-26
NP153 | 5.6 Transport and Communications | TC1 Village Travel Plan | 58 | Comment | The consideration of an eastern link roadwillencourgae large scale development and possibly fill in between the A41 and Malpas | Noted, this is a valid point. Explicit reference to a "link road" will be removed - see comment below. | N | 2014-03-01
NP3 | 5.6 Transport and Communication | TC1 - TC 3 Aspirations | 59 | Wording Change bullet point 1 | 1/ A new link road, if appropriate need is identified, to the east of the village (i.e. potentially linking Tilston Road / Chester Road / Well Street or parts thereof) to ease congestion in the Village Centre. | 1/ Opportunities need to be identified to ease congestion in the village centre | Y | 2014-01-09
NP5 | 5.6 Transport and Communication | TC1 - TC 3 Aspirations | 59 | Wording Change bullet point 5 | 5/ Better publicity and promotion of bus services to encourage greater use by residents, which will support improvements to services | 5/ Better Bus services to encourage greater use by residents which will support improvements to services | Y | 2014-01-09
NP6 | 5.6 Transport and Communication | TC1 - TC 3 Aspirations | 59 | New aspiration to be added | Pedestrian Crossings on High Street and Chester Road are required | This will be added. | Y | 2014-01-09
NP8 | 5.6 Transport and Communication | TC1 - TC 3 Aspirations | 59 | New aspiration to be added | Put double yellow lines down at least one side of the High Street. This will help traffic flow and have little effect on shop sales | We will recommend that this is considered by CW&C | Y | 2014-01-16
NP96 | 5.6 Transport and Communications | TC3 | 59 | ? | Not sure this policy will deliver pedestrian or cycle routes because of the existing village landscape topography and village street scene structure | The policy refers to relatively short connections from housing sites on the edge of the village into the villlage centre. These can be delivered and are important, regardless of topography. | N | 2014-02-19
NP97 | 5.6 Transport and Communications | TC3 Explanation | 59 | ? | Issues of pedestrian and cycle linkage have been highlighted in the context of the wider parish, but not specifically about the relationship with potential housing development | This will be added. | Y | 2014-02-19
NP113 | 5.6 Transport and Communications | Community Priorities | 59 | Addition information | I think somewhere in the document we should have " investment in public transport improvements listed as a priority.. There is mention of improving the publicity but the fact is nobody would choose to use the current service unless, like me, they had no alternative. | We will add this as an aspiration. In reality this would be largely dependent on the bus operators and it would be difficult to effect an improvement in services. An increased population in Malpas, and greater bus use, will make increasing services more commercially attractive. | Y | 2014-02-22
NP158 | 5.6 Transport and Communications | TC3 Pedestrian and Cycle Routes | 59 | Comment | Pavements for pedestrians on roads which are to be link roads. This is crucial for safety. | Agreed - but TC3 is about new residential roads and pedestrian connections; not the link road. It will be stated that all new roads should have pavements. | Y | 2014-03-05
NP98 | 5.6 Transport and Communications | Other Aspirations | 60 | ? | Also need to include reference to parking issues on the bend outside the Heber High School | Agreed. | Y | 2014-02-19
NP148 | 5.6 Transport and Communications | Other Aspirations | 60 | Question | Last bullet point - Should this be a specific policy somewhere? | This could not be linked to a policy - there is no reasonable requirement to ask applicants to provide parking spaces for existing houses. | N | 2014-02-22
NP23 | Figure 5.1 Proposals Map |  | 61 | Missing Key | On the inset there is red line that has no explanation. | This is suggested alignment of the Roman Road- Figure 5.2 for further detail. The red line will be taken off Figure 5.1. | Y | 2014-01-19
NP99 | Figure 5.1 Proposals map |  | 61 | Missing data | Items 35, 36 and 40 from appendix E not indicated on figure 5.1 the proposals Map | These will be added. | Y | 2014-02-19
NP100 | 6. Making it Happen |  | 63 | Whole paragraph | For the final version this page will need to be re-written to document the review process. Probably needs a new section heading as well. | Yes, this will be updated. | Y | 2014-02-19
NP101 | 6. Making it Happen | After Adoption | 63 | Word change | 2nd paragraph the phrase in brackets " Which can only react to planning) - React does not to be the right word in this context | Will change "react" to "respond" | Y | 2014-02-19
NP102 | 6. Making it Happen | After Adoption | 63 | Wording change | 2nd paragraph - Suggest re-wording to "The "aspirations" in section 5 provide useful cues to the construction of a set of actions for the Parish Council to follow up on. | Agreed - will add this alongside existing text. | Y | 2014-02-19
NP103 | 7. References |  | 64 | Question | How do we reference these documents against the finished Neighbourhood Plan. Is it a on line appendix which contains relevant local documents and links to the other existing documents and web sites? | The References in the printed final NP will appear as they do here. The Steering Group could create an online version with links - this would be useful. | Y | 2014-02-19
NP105 | Appendix B | Glossary Affordable Homes | 73 | Explanation required | The word "median" needs explaining or an indicative value adding. | "Median" is used here as it is part of the standard definition of "Affordable Housing" which needs to be replicated exactly. "Median" is a standard and commonly used statistical term - essentially meaning the middle of a series of a values (i.e. it differs from "average" by not being skewed by the number of instances of a value). We do not feel that the Glossary is required to define other terms used within the glossary entries and "median" has a standard definition and is found in all dictionaries. An indicative value can certainly not be set here as household income will vary frequently over time, i.e. with inflation and economic trends, and will change significantly during the life of the NP. | N | 2014-02-19
NP112 | Appendix B | Glossary of terms and acronyms | 73 | move | I think the glossary needs to be at the beginning of the document or at least the first appendix | Glossaries are typically found as an appendix at the end of documents (for example in Local Plans). We will make it Appendix A. | Y | 2014-02-22
NP149 | Appendix B: Glossary of Terms and Acronyms |  | 73 | Change of wording | Neighbourhood Forum - this should be amended to read “: the body responsible for producing a Neighbourhood Plan……..” | This will be revised (see comment NP64). | Y | 2014-02-26
NP106 | Appendix C | Key associated with the Map | 75 | Explanation required | Abbreviations on the map need to be explained | We will add these. | Y | 2014-02-19
NP30 | Appendix D | Character Buildings and Structures | 76 | Data error | In Appendix D on page 76 there is a list of listed buildings - Broselake Cottage is not a listed building. | Broselake Cottage is identified as a Grade II listed building on English Heritage's National Heritage List website (listed as "Brose Lake Farmhouse"). See: http://list.english-heritage.org.uk/resultsingle.aspx?uid=1330252&searchtype=mapsearch I will amend the reference to"Broselake Farmhouse". If anyone feels this is incorrect I suggest they contact EH. | N | 2014-02-05
NP107 | Appendix D | In the surrounding area | 76 | Re-aligning of buildings | Move Broselake Farm to number 14 in the Key listed buildings above | This list will be reviewed to list all listed buildings in the area. | Y | 2014-02-19
NP108 | Appendix D | In the surrounding area | 76 | Re-aligning of buildings | Broselake Cottage is not a listed building Move to number 13 in the Malpas Village list and renumber the rest accordingly. Also amend figure 5.1 the Proposals Map | See above comments. | N | 2014-02-19
NP109 | Acknowledgements | In the surrounding area | 80 | Additional information | Add "Nomansheath Parish Council" to two Names on the list - Peter Guildford and Paul Roberts | Agreed | Y | 2014-02-19
NP110 | Whole document | all | 80 | Additional information | Needs a local contact person for queries i.e. Any queries please Contact Clerk Malpas Parish Council | For Steering Group to respond | Y | 2014-02-19
NP11 | 5 Policy section | All themes | 18 - 60 | Question | The numbering of Objectives do not follow on: e.g. 1, 2, 3, 9,10. Is this deliberate? | Yes - this shows the objectives from Section 4 they are being met. This will be explained. | Y | 2014-01-19
NP33 | 5.1 Homes for all | H4 | 23-24 | Houses per development | Congratulations on a well planned and produced Neighbourhood Plan. My only comment is to do with the size of future planning of properties. Can these be restricted to no more than 35 houses per development. Obviously the smaller the groups the better to fit into Malpas. | Thank you. This comment is dealt with in Policy H4. | N | 2014-02-17
NP67 | 5.2 Built Character and Local Environment | BE1 | 27-28 |  | Where is the local people's say in the discussion on how the design of buildings should look? | Policies in the NP require high quality design that responds positively to the character of the local area. These policies are the subject of this local consultation exercise. The character of the area has been defined by the Malpas Character Study which was itself subject to local consultation. The role of the NP is not be prescriptive on design but to establish a framework against which designs will be assessed. The policies here must be interpreted by planning officers, and by Members at planning committee, who should be reflecting local views. | N | 2014-02-19
NP24 | Figure 5.1 Proposals Map | Appendix E | 51 & 78 | Missing locations | Items 35, 36 and 40 not indicated on figure 5.1 the proposals Map | These will be added. | Y | 2014-01-19
NP25 | Figure 5.1 Proposals Map | Appendix E | 51 & 78 | Additional Green Space | There is also pond on the south side of Church Street. It is used for fishing and we can get to it along the footpath from Parbutts lane that goes along the back of houses on Church Street. Add the pond to the Green Spaces list | This will be added. | Y | 2014-01-19
NP18 | 5.6 Transport and Communications | Issues and Opportunities | 55-57 | Additional data required | Taxis - there is no mention of the lack of Taxis. | We will refer to this in the issues section but this is a commercial factor that the NP will not be able to influence. | Y | 2014-01-19
NP19 | 5.6 Transport and Communications | Issues and Opportunities | 55-57 | Additional data required | Emergency services - the Plan only mentions the fire service. No mention of how far away Chester hospital is, nor the police. No mention of first responders. Some money to keep the fire station open would also be important. Also Whitchurch police station is nearby but we do not get served by it. There is minor injuries unit in Whitchurch but we have no say in its development. | These matters are not related to land-use or development and so lie outside the scope of the NP. The fire station is mentioned because it is an existing land-use. These issues could be pursued by the Parish Councils. | N | 2014-01-19
NP20 | 5.6 Transport and Communications | Issues and Opportunities | 55-57 | Additional data required | Cycling - this is briefly mentioned but not really covering how dangerous the roads are to cyclist particularly for teenagers. It is not surprising that cycling to the Heber is so low with such dangerous roads. One aspiration not mentioned which has happened elsewhere is converting the old railway into a cycle route. This could form a safe cycle route to Whitchurch and may even allow an safe cycling alternative to Chester. Connecting the old railway line and the canal towing path may form access to a number of places (I know there are bylaws about cycling on towing paths). | We will expand the text on cycling to cover this. | Y | 2014-01-19
NP104 | Appendix A |  | 71-71 | colour change | Consider re-colouring the blocks. I.e. Green least appropriate Orange more appropriate Red least appropriate | Green sites for least appropriate is intended to translate as sites that should be kept "green". Also green for most appropriate could imply "go" (i.e. development of the site is supported) when the site could be unsuitable for other reasons (e.g. Housing numbers). Also need to consider colours that enable the text to be read easily. The colours will be left as they are. | N | 2014-02-19
NP111 | Whole document | all | Various | Rename | Malpas Village Design Statement should be indicated as a "draft" document | See comment NP124 |  | 2014-02-22
NP155 | All Policy sections | All | various | Additional authority | When adopted, the Neighbourhood Plan becomes the responsibility of the The Parish Council, so they should also be included in any discussions where reference is made to any negotiations between Developers and the Local Authority as being appropriate. | The Parish Council (s) will continue to be non-statutory consultees on planning applications. We will adapt policies to require developers to engage with the Parish Councl, where appropriate. | Y | 2014-03-04
NP156 | All Policy sections | All | various | Policy Wording | All policise should be more directive with the view to controlling dveleopment. E.g. "must conform to" - "must respect", etc. | This has also been discussed with CW&C. Policy wording will be amended where necessary. | Y | 2014-03-05

## NP General Comments
Change Request Number | NP Section | Policy / Area Affected | Page | Comment | Response | Action taken if any | Date raised | Accepted / Reason for Rejection | Submitter informed
GNP1 | All | Policy sections |  | I congratulate the group on having produced a workmanlike document. But, by being so brief, it suffers from a shortage of hard facts and numbers. I have scanned the Malpas plan site and this is better in this respect but overall I find the proposals rather timid. | The "hard facts and numbers" are found in the separate Evidence Base document. Policy wording will be reviewed. |  | 2014-01-14
GNP2 | All |  |  | It is an impressive piece of work. People have obviously given a great deal of time and thought to the project. | Noted with thanks. |  | 2014-01-16
GNP3 | 5.3 Landscape Character and the Natural Environment | Voice of the Community | 39 | You say that "97% agree that new development should increase opportunities for carbon reduction by the promotion of green industries, green energy sources and sustainable transport choices". I have looked at "Green energy sources" and find that the UK Department of Energy and Climate Change has a 2013 report off forecast generating costs for fossil fuel and "Green" sources of electricity on their website. I enclose an extract from their report. The report is not clear about whether the cost is at the point of generation or at the point of use. This is crucial as about 30% of the users cost of electricity is the cost of distribution. The National Grid design is based on the use of large generating stations located within reasonable distance of the end users. Large scale wind farms will be more distant from users and will need large investments in additional distribution; more pylons and overhead cables for people to protest about! I am pleased to see that Nuclear is forecast to be economically attractive. Nuclear does not need much additional investment in distribution and produces a lot of energy in a small area compared with wind and large scale solar. | This is interesting but beyond the scope of the NP. The NP supports the use of solar panels, heat pumps etc at a domestic scale and seeks to influence the siting and design of wind turbines. |  | 2014-01-16
GNP4 | 5.2 Built Environment and Local Character | Whole section | 26-32 | I feel the rate of growth of Malpas should be much faster. The Economist articles I sent you explain why I hold this view. | This is an interesting view, which has not been shared by other respondents during consultation on the NP. |  | 2014-01-16
GNP5 | All | Whole document |  | Despite the general sensible comments on future architecture, facilities, etc. nothing can disguise the parochial Council's failure to produce a robust plan limiting the future development of the village to a number of houses which will not destroy the present precarious balance where the High Street is overwhelmed with traffic. This failure has allowed speculative building applications all round Malpas. Please produce a proper plan now. | Unfortunately the NP is not able legally to restrict housing growth below numbers set out in the Local Plan. The time taken for CW&C to adopt the Local Plan, and their current lack of a 5 year supply has led to the current level of residential applications. The NP aims to influence what it can within the scope in which it can operate. |  | 2014-01-17
GNP6 | All |  |  | I have read through the Neighbourhood Plan and I thought that it was an excellent document, and the whole team should be congratulated on its production | Noted with thanks. |  | 2014-01-19
GNP7 | 5.6 Transport and Communications | TC1 Village Travel Plan |  | I would like to contribute to the Malpas Travel Plan. The lack of taxis, buses and safe walking and cycle routes has an impact at one end. Rail travel at Whitchurch and Chester are impacted by regional developments such as Northern Hub and national developments such as HS2. HS2 would have a fairly local impact because it would allow capacity on the West Coast main line for direct London trains from Shrewsbury and maybe Wrexham. | This comment has been passed to the Travel Plan team. |  | 2014-01-19
GNP8 | All |  |  | I would like to congratulate the residents group who have put together this plan. It is essential that we plan carefully for our lovely village if we are to preserve all its qualities. Protection of our village against developers who do not want to work with the community and have little regard to its ability to cope is essential Thank you to the efforts you have made in protecting my heritage | Noted with thanks. |  | 2014-01-21
GNP9 | The Executive Summary | Policy section summary |  | The leaflet should have page numbers for reference | Noted - the leaflet has now been printed and will not be amended. |  | 2014-01-21
GNP10 | The Executive Summary | Housing |  | In no way should the extent of the new housing be exceeded. Malpas is suffering enough from ruthless development. Take a look at Tilston Road - the absurd pavement narrowing the road to single traffic, the poor quality of the new builds on the right and left, the destruction of healthy beech and evergreen trees on the grounds of The Beeches, the water flowing off what was once a walled garden. - Need I go on? | Noted. |  | 2014-01-21
GNP11 | The Executive Summary | General |  | This plan needs to go back to the drawing board. It is too clichéd and appears to contains veiled comments. Re P1 C there is no reference to the agricultural aspect of Malpas. It is far too urban in flavour. | The Executive Summary leaflet can only give a brief flavour of the NP. The NP does deal with both the village and surrounding rural area. |  | 2014-01-21
GNP12 | The Executive Summary | Homes for All |  | "A preference for development on Brownfield sites before Greenfield site" No - adding a field or two to development as been the case to date | What has happened to date cannot be blamed on the NP. The NP clealry favours brownfield development over greenfield development but policies will only be able to react to planning applications as they come inm whether they are on grenfield or brownfield sites. |  | 2014-01-21
GNP13 | The Executive Summary | Homes for All |  | "The extent of new housing to be in line with Cheshire West and Chester Council Local Plan, but may be exceeded if significant local benefits are delivered as part of a scheme" - absolutely not | This element of the policy is now being removed. |  | 2014-01-21
GNP14 | The Executive Summary | Homes for All |  | " Dwellings will be built to quality and energy efficiency standards" - No guarantee of this please see comments | This is an aim of the NP and is expressed in policies and aspirations. |  | 2014-01-21
GNP15 | The Executive Summary | Built Environment and Local Character |  | First 4 bullet points scribbled out - This is nonsense. - Building destroys character, It cannot enhance it. | We disagree. There are many examples, across the UK, of well designed new buildings that have enhanced local character. Places are dynamic and need to change over time. This change needs to be managed positively. |  | 2014-01-21
GNP16 | The Executive Summary | Landscape Character and the Natural Environment |  | New development proposals will preserve and enhance the existing landscape character - The character of Malpas was destroyed when St Joseph's was allowed to close | We cannot comment on the closure of St Joseph's - this is outside the scope of the NP and occured before it was drafted. |  | 2014-01-21
GNP17 | The Executive Summary | The Local Economy |  | Support for expansion of local tourism through appropriate developments. - Not necessary. | Tourism offers the potential for significant economic benefits which are considered important. |  | 2014-01-21
GNP18 | The Executive Summary | How can you help? |  | Incomplete information. Surnames required. | This leaflet has already been issued. |  | 2014-01-21
GNP19 | All |  |  | We've read the draft Malpas Plan and agree with everything it proposes. Can we follow Tattenhall's example and have a referendum as soon as possible? Assuming the majority acceptance vote, it would be beneficial in keeping rapacious developers in check | Noted. We hope to take the NP to Referendum as soon as possible - there are several stages we need to pass before then. |  | 2014-01-22 |  | Responded to
GNP19 | All |  |  | Many thanks for addressing the St. Oswald's Council meeting on Monday. We are all appreciative of the time and effort you and your colleagues spend on our behalf | Noted with thanks. |  | 2014-01-22 | Yes | Yes
GNP20 | All |  |  | Chris, Thanks for the information about the change log. It never ceases to amaze me how little some people appreciate the amount of effort that has gone into this document. The approach being taken indicates that it is intended to be a live document. No matter what anyone else says the whole team is to be congratulated on the good well done. | Noted with thanks. | Thanked individual for their support | 2014-01-24
GNP21 | All |  |  | In general, all seems well. However, Malpas does not want to attract large developments. We do not need a large Supermarket here as that would encourage large scale development. I would not like to see Malpas end up like Frodsham or Winsford | Noted. There are no proposals in the NP for a large supermarket or similar scale development. |  | 2014-01-31
GNP22 |  |  |  | Affordable housing needs to be for local people not families from outside | It is not possible to make this restriction through planning policy. Policy H3 however will ensure that affordable housing matches the needs that have been identified locally. |  | 2014-02-01
GNP23 |  |  |  | Concern expresse3d with regard to traffic on High Street and Church Street | The Village Travel Plan will address traffic through the village. |  | 2014-02-01
GNP24 |  |  |  | Concerned about flooding on Well Street and on the village as a whole | Existing legislation deals comprehensively with drainage, there is nothing the NP can usefully add to this. |  | 2014-02-01
GNP25 |  |  |  | Concerned about the impact on school re numbers of children from new developments | Significant new developments will be required to address their impacts (e.g through section 106 payments to the school to enable expansion). This is covered by existing planning policy, and by Policy SF4 of the NP. |  | 2014-02-01
GNP26 |  |  |  | Should include a reference to community rainwater harvesting | This could be added as an aspiration - for Parish Cuncil to consider |  | 2014-02-01
GNP27 |  |  |  | Should include reference to cycle only ways especially to schools and village centre | Cycleways are covered in TC3 and also within the Village Travel Plan. |  | 2014-02-01
GNP28 |  |  |  | Should include references to relief road and infrastructure support | This is considered in the Village Travel Plan. |  | 2014-02-01
GNP29 |  |  |  | Sustrans (cycle ways) in the Bristol / Bath area have used old railway tracks make on off-road route along the line of our old railway track | This will be considered and a reference added. |  | 2014-02-01
GNP30 |  |  |  | A41 is not big enough for the traffic it carries | This is a fair comment, but needs to objectively assessed. It is beyond the scope of the NP. |  | 2014-02-01
GNP31 |  |  |  | Encourage cycling on short journeys to the village | Agreed, this would be beneifial. It will be added to the issues and opportunities part of Secion 5.6. |  | 2014-02-01
GNP32 |  |  |  | New builds should include green energy requirements | This is already covered by existing planning policy. |  | 2014-02-01
GNP33 |  |  |  | Malpas needs to be sustainable | Agreed - this is a fundamental aim of the NP. See the Vision and Objectives (Section 4). |  | 2014-02-01
GNP34 |  |  |  | Builders should contribute to Astroturf at the Heber school and to improvement of the Recreation Ground particularly the MUGA area for basketball | Noted - the community's priorities for sports and leisure provision are set out on p49. |  | 2014-02-01
GNP35 | All |  |  | Chris, A good document. Many thanks to all involved. It still doesn’t answer the point as to why Shropshire could get its act together and yet CW&C couldn’t. That is why the Tesco Store application in Whitchurch failed, and why Tesco is still apparently pondering its next move. End result Gladman didn’t win, CW&C put through its own goal. Localism – my –XXX. Its time that Mr Obrien was moved from his far too safe seat, then he’ll really know what localism means. | Noted (!) |  | 2014-02-02
GNP36 | All |  |  | I moved to the village 20 years ago from Huntington Chester as the area around there was becoming more built up and retail outlets were planned and have since been built. I also moved to the village to live with my now husband who has lived in Malpas all of his life and wanted a rural / small village atmosphere where you actually knew your neighbours not pass people in the street. For the last 20 years Malpas provided me with exactly what I was looking for, but feel that once the new proposed developments are erected Malpas will lose the reason why I moved here. If I wanted to live amongst a large housing development in a town I would have stayed in Chester!! The green belt land is slowly being taken away from the village. I am all for small developments as the population expands, but these houses are going to be for people moving into the area and are either too expensive or social housing for people outside the Malpas area and how will this benefit the residents? Correct me if I am wrong, but I believe Malpas had to provide an additional 200 houses before 2030 and we have now surpassed that target with existing planning applications approved and houses already built and it is only 2014!!! So why do we need and are accepting such large developments where will it stop? The High Street is already a nightmare. On a daily basis snarl ups occur all of the time and this is not just at school times. These blockages in the village will only be exacerbated by the extra traffic associated with the large quantity of properties planned. Also, the council are proposing to charge parents nearly £1000 a year to bus their children to the Heber so lots will drive instead how many more cars will this be? The schools will be pushed to cope with the extra influx of children, so to get planning through and create more spaces the council have decided to change the catchment areas for the Heber leading existing feeder schools such as Tattenhall to be pushed to go to Christleton High school. It is with great sadness that I have to watch our village be terrorised by greedy builders and turned from a pretty country village into a sprawling town. I hope that villagers opinions are listened to, not that it will have an impact, as I am sure the powers that be have already made their decisions and this is all just a formality they have to follow. | Noted. The land around Malpas is open countryside rather than Green Belt but we understand your point. The draft Local Plan does indeed propose 200 new homes for Malpas and more than 300 have now been granted planning permission. This is due to a number of factors: the new National Planning Policy Framework, the fact that CW&C has an outdated District Plan and has not yet adopted the Local Plan and the fact that they do not have a currently identified 5-year housing supply. These are all issues beyond the remit of the NP, unfortunately. The Village Travel Plan, which is introduced in the NP and is currently being progressed will consider transport impacts in the village holistically - including new developments and the Bishop Heber school. |  | 2014-02-03
GNP37 | All |  |  | The key will be our ability to influence plans that have been approved in outline form. How will CWaC support Malpas now that we have more houses than the Local Development Framework has first calculated. Keep on supporting the NP | Agreed - there is scope to influnce the design of approved developments when reserved matters applications are made. Interesting point about CW&C and housing numbers - we will need to follow this issue and see what the final Local Plan says. |  | 2014-02-07
GNP38 | All |  |  | Just to say that I support the Neighbourhood Plan set out for Malpas, and that we do not need much new housing in the village | Noted. |  | 2014-02-12
GNP39 | All |  |  | I am disgusted and shocked at the planning. Malpas will be completely ruined as a village and the community feeling will be lost. Far too many houses passed all at once. Planners do not care how people feel regarding this planning. | Noted - but this is beyond the scope of the NP. See comment GNP36 above. |  | 2014-02-12
GNP40 | All |  |  | The Neighbourhood Plan supports the housing target of 200 new homes in Malpas over the Local Plan period 2010 - 2030 as proposed by Policy STRAT8 of the Local Plan. Foul flows from these developments would flow to Malpas Waste Water Treatment Works, where there is sufficient capacity available to accommodate the flows generated. Whilst the Neighbourhood Plan doesn’t allocate individual sites for housing, DCWW support the aims of policy H1 New Housing to direct sites towards sustainable locations. We are aware that planning permissions have recently been grated for residential development for 200 units in Malpas at two sites, at Land between Chester Road and Well Street for 140 units, and at West End Poultry Farm for 60 units. A further two planning applications are awaiting determination by the Local Planning Authority for 41 units at Land off Chester Road, and for 19 units at Mount View Farm. These recent planning permissions and applications have been factored into our assessment. | Noted. This is useful information. |  | 2014-02-18
GNP41 | All | All |  | Somebody has done an incredible amount of work | Noted with thanks. |  | 2014-02-22
GNP42 | All | All |  | The Plan is clearly written and easily understood. The Plan succinctly sets out the challenges for Malpas and acknowledges that the village has grown incrementally over time and that this should continue in the future. The overall approach adopted within the Plan is one that clearly seeks to support and allow development on those sites which benefit from a good location in terms of proximity to the centre of the village and which provide or contribute towards the provision of services facilities and other infrastructure associated with new development. This approach is strongly supported and should be carried forward as a key theme in future iterations of the plan. | Noted with thanks. |  | 2014-02-23
GNP43 | 4. Vision and Objectives |  | 17 | The vision for Malpas is welcomed along with clear linkages between maintaining a thriving and sustainable village and the need for sustainable development that integrates well with the village. | Noted. |  | 2014-02-23
GNP44 | All |  |  | Malpas Alport schoolcan't support many more pupils. It is also lacking in green filed space | Noted but we require a quotable source before we can add this to the evidence base. |  | 2014-03-01
GNP45 | All |  |  | Roads inadequate around Malpas Shopping areato takemore school traffic. - Don't spoil the existing village | Noted. This is an issue for the Village Travel Plan. |  | 2014-03-01

## Completed Change Requests
Change Request Number | NP Section | Policy / Area Affected | Page | Change request | From | To | Benefit of Change | Raised By | Contact number/e-mail | Date raised | Accepted / Reason for Rejection | Date change to be implemented